## Impact Matrix
Object | Type | Impact | Layer | Risk | Owner | Rationale
rcm.dim_patient | table | No Change | dimension | low |  | Provides the attribute. rcm.sp_load_ar_fact already joins rcm.dim_patient as 'p'.
rcm.fact_ar | table | Modify | fact | medium |  | Add column patient_financial_class (existing join).
rcm.sp_load_ar_fact | stored_procedure | Modify | warehouse | medium |  | Populate rcm.fact_ar.patient_financial_class in the INSERT and SELECT lists.
rcm.vw_ar_detail | view | Modify | warehouse | low |  | Expose patient_financial_class to the reporting layer.
rcm.vw_ar_aging_summary | view | Review | warehouse | medium |  | Aggregate view: adding patient_financial_class would change the grain, so it needs a business decision rather than an automated edit.
df_rcm_ar | dataflow | Refresh | reporting | low |  | Reload the dataflow so the new column lands in the dataset.
pb_ar_aging | dataset | Refresh | reporting | medium | RCM Analytics | Refresh the semantic model to pick up the new column.
AR Aging Report | report | Modify | reporting | low | RCM Analytics Team | Surface the new column on the impacted visuals.
lambda_run_ar_load | lambda_function | Review | etl | low |  | lambda_run_ar_load invokes rcm.sp_load_ar_fact; confirm the orchestration still succeeds after the change.
lambda_refresh_powerbi_dataset | lambda_function | Review | etl | low |  | lambda_refresh_powerbi_dataset refreshes pb_ar_aging; confirm the orchestration still succeeds after the change.
sfn_rcm_nightly | step_function | Review | etl | low |  | sfn_rcm_nightly orchestrates lambda_run_ar_load; confirm the orchestration still succeeds after the change.

## Lineage Path
Step | Object | Type | Layer
1 | rcm.dim_patient | table | dimension
2 | rcm.sp_load_ar_fact | stored_procedure | warehouse
3 | rcm.fact_ar | table | fact
4 | rcm.vw_ar_detail | view | warehouse
5 | pb_ar_aging | dataset | reporting
6 | AR Aging Report | report | reporting

## Power BI
Target | Type | Action | Detail
pb_ar_aging.AR Detail | dataset_table | Add column | Add 'patient_financial_class' from rcm.vw_ar_detail to table 'AR Detail'.
pb_ar_aging | dataset | Refresh semantic model | Import model on schedule 'Daily 05:30 ET' must be refreshed before the column appears.
Total AR Balance | measure | Validate | Measure sits on the modified table; confirm totals are unchanged after the refresh.
Total Charges | measure | Validate | Measure sits on the modified table; confirm totals are unchanged after the refresh.
Total Payments | measure | Validate | Measure sits on the modified table; confirm totals are unchanged after the refresh.
Total Adjustments | measure | Validate | Measure sits on the modified table; confirm totals are unchanged after the refresh.
Total Denials | measure | Validate | Measure sits on the modified table; confirm totals are unchanged after the refresh.
AR Over 90 Pct | measure | Validate | Measure sits on the modified table; confirm totals are unchanged after the refresh.
Aging Summary / v_summary_matrix (matrix) | visual | Review field placement | Candidate visual for surfacing 'Patient Financial Class'.
Aging Summary / v_balance_card (card) | visual | Review field placement | Candidate visual for surfacing 'Patient Financial Class'.
AR Detail / v_detail_table (table) | visual | Review field placement | Candidate visual for surfacing 'Patient Financial Class'.
Payer Analysis / v_payer_bar (clustered_bar) | visual | Review field placement | Candidate visual for surfacing 'Patient Financial Class'.
Payer Analysis / v_payer_slicer (slicer) | visual | Review field placement | Candidate visual for surfacing 'Patient Financial Class'.
AR Aging Report | report | Publish validation | Publish to the workspace and compare totals against the pre-change snapshot.

## Tests
Suite | Test | Category | Status | Expectation | Observed
unit_tests_patient_financial_class | column_population | Column Population | passed | at least one populated row | 12
unit_tests_patient_financial_class | null_validation | Null Validation | passed | 0 records | 0
unit_tests_patient_financial_class | row_count_validation | Row Count Validation | passed | matches the source row count from staging.stg_ar_transactions | 12 vs 12
unit_tests_patient_financial_class | duplicate_validation | Duplicate Validation | passed | 0 records | 0
unit_tests_patient_financial_class | datatype_validation | Data Type Validation | passed | 0 records exceeding VARCHAR(50) | 0
unit_tests_patient_financial_class | domain_validation | Domain Validation | passed | 0 records outside the certified domain | 0
unit_tests_patient_financial_class | source_to_target_parity | Source to Target Validation | passed | 0 records where the fact value differs from the source dimension | 0
unit_tests_patient_financial_class | view_exposure_vw_ar_detail | Reporting Layer Exposure | passed | view compiles and exposes the new column | 12
integration_tests | reconciliation::rcm.fact_ar row count | Financial Reconciliation | passed | unchanged before and after | before=12.00 after=12.00 delta=0.00
integration_tests | reconciliation::rcm.fact_ar SUM(charge_amount) | Financial Reconciliation | passed | unchanged before and after | before=27,921.50 after=27,921.50 delta=0.00
integration_tests | reconciliation::rcm.fact_ar SUM(payment_amount) | Financial Reconciliation | passed | unchanged before and after | before=17,075.00 after=17,075.00 delta=0.00
integration_tests | reconciliation::rcm.fact_ar SUM(adjustment_amount) | Financial Reconciliation | passed | unchanged before and after | before=4,356.50 after=4,356.50 delta=0.00
integration_tests | reconciliation::rcm.fact_ar SUM(denial_amount) | Financial Reconciliation | passed | unchanged before and after | before=1,820.00 after=1,820.00 delta=0.00
integration_tests | reconciliation::rcm.fact_ar SUM(balance) | Financial Reconciliation | passed | unchanged before and after | before=6,490.00 after=6,490.00 delta=0.00
integration_tests | reconciliation::rcm.fact_ar DISTINCT(claim_id) | Financial Reconciliation | passed | unchanged before and after | before=12.00 after=12.00 delta=0.00
integration_tests | reconciliation::rcm.vw_ar_detail row count | Financial Reconciliation | passed | unchanged before and after | before=12.00 after=12.00 delta=0.00
integration_tests | reconciliation::rcm.vw_ar_detail SUM(balance) | Financial Reconciliation | passed | unchanged before and after | before=6,490.00 after=6,490.00 delta=0.00
integration_tests | reconciliation::rcm.vw_ar_aging_summary row count | Financial Reconciliation | passed | unchanged before and after | before=4.00 after=4.00 delta=0.00
integration_tests | reconciliation::rcm.vw_ar_aging_summary SUM(total_balance) | Financial Reconciliation | passed | unchanged before and after | before=6,490.00 after=6,490.00 delta=0.00
integration_tests | parity::rcm.vw_ar_detail::balance | Reporting Parity | passed | equals COALESCE(SUM(balance), 0) from rcm.fact_ar | 6490 vs 6490
integration_tests | parity::rcm.vw_ar_detail::row_count | Reporting Parity | passed | equals the row count of rcm.fact_ar | 12 vs 12
integration_tests | parity::rcm.vw_ar_aging_summary::total_balance | Reporting Parity | passed | equals COALESCE(SUM(balance), 0) from rcm.fact_ar | 6490 vs 6490

## Reconciliation
Metric | Before | After | Delta | Result
rcm.fact_ar row count | 12 | 12 | 0 | PASS
rcm.fact_ar SUM(charge_amount) | 27921.5 | 27921.5 | 0 | PASS
rcm.fact_ar SUM(payment_amount) | 17075 | 17075 | 0 | PASS
rcm.fact_ar SUM(adjustment_amount) | 4356.5 | 4356.5 | 0 | PASS
rcm.fact_ar SUM(denial_amount) | 1820 | 1820 | 0 | PASS
rcm.fact_ar SUM(balance) | 6490 | 6490 | 0 | PASS
rcm.fact_ar DISTINCT(claim_id) | 12 | 12 | 0 | PASS
rcm.vw_ar_detail row count | 12 | 12 | 0 | PASS
rcm.vw_ar_detail SUM(balance) | 6490 | 6490 | 0 | PASS
rcm.vw_ar_aging_summary row count | 4 | 4 | 0 | PASS
rcm.vw_ar_aging_summary SUM(total_balance) | 6490 | 6490 | 0 | PASS